## Sheet1
PRODUCT BACKLOG
NO. | TASK INFO | SPRINT | PRIORITY | STATUS
1 | Implement the basics graphic UI interface for the board game, that is consists of the game board of dimensions 10x10 with each division being a square. | 1st week |  | COMPLETED
2 | Each square in the board is numbered for orientation purposes, which would enable user for ease of keeping track of the pawn position. | 1st week |  | COMPLETED
3 | Create the necessary buttons in th UI for the game. | 2nd week | HIGH | COMPLETED
4 | Provide dialog boxes for users to enter details. | 2nd week | HIGH | COMPLETED
5 | Implement the start game function which includes identifying the order of players to roll and the color of each players pawn. | 2nd week | HIGH | COMPLETED
6 | Implement a fucntion that randomizes the portal, time machine and the bounty tile occurances on the board. | 2nd week | MEDIUM | COMPLETED
7 | Implement the portal function. | 2nd week | MEDIUM | COMPLETED
8 | Implement the time machine fucntion . | 2nd week | MEDIUM | COMPLETED
9 | Introduce the graphics to support the player pawn to move through the board. | 2nd week | HIGH | COMPLETED
10 | Provide queries for updating and creating new user profiles in the database system. | 3rd week | HIGH | Planned
11 | Deploy the button for displaying the score report and implement the back end logic of it. | 3rd week | HIGH | Planned
12 | Implement a function that will make the player to choose which pawn to move. | 3rd week | MEDIUM | Planned
13 | Implement the bounty tile function. | 3rd week | MEDIUM | Planned
14 | Implement a randomize fucntion that would provide bounty cards to the player. | 3rd week | MEDIUM | Planned
15 | Implement the function for each bounty card. | 3rd week | MEDIUM | Planned
16 | Implement Test cases to test the game. | 3rd week | LOW | Planned